# ANNUAL ADMINISTRATIVE SERVICES PROGRAM REVIEW AND PLANNING PROGRESS

Vice President

# FALL 2008

- What is the status of the objectives identified in your Fall 2006 Action Plan: Program Priorities and/or your Fall 2007 Annual Progress Plan? Please be as complete as possible. Add rows as necessary:

| OBJECTIVE | COMPLETED, REVISED, IN PROGRESS, ETC. | COMMENTS |
| --- | --- | --- |
| Coordinate planning for all major campus remodeling projects. | Planning for the core and art remodels is complete. Planning for the science area remodel for nursing/EMS and for student services is in progress. | Phasing of these projects and temporary locations for displaced departments (“swing space”) will continue to require attention. |
| Actively participate in the tutoring and African American student support program projects. | Both projects have moved from the planning stage and into implementation. | The level of student participation in both the Umoja Scholars and Tutoring Programs is high. Both programs will be evaluated during the early stages to direct further development. |
| Provide support for the accreditation review process and the creation of the self study | Completed, due in large part to excellent work by the Accreditation Liaison Officer. | Appears to have resulted in a very positive review and report by the visiting team, along with a number of recommendations that will require attention beginning in Spring 2009. |

| Support the development of a system for tracking student prospects and fulfilling requests for information about college programs and services | This project, envisioned by the previous Director of Marketing and Communications, has changed as a result of other demands on that department and the recommendations in the Clarus report. | Initial steps have been taken to respond to Clarus recommendations, including the creation of materials to be used consistently when responding to inquiries. |
| --- | --- | --- |
| Coordinate the development of a new facilities master plan. | Completed during 2007-08. | A final phase of overall site planning is now needed. |
| Provide leadership for enhanced integration and coordination among all of the college student services programs. | The planning work needed in student services is essentially complete, with only the final phases of the related facilities plan to finish. | Excellent work by the student services managers and the faculty and staff on the Student Services Advisory Committee resulted in a commendation from the visiting accreditation team. |

- What are new objectives that you have identified as a result of changes in the environment, data or other since Fall 2007?

| OBJECTIVE | ACTIVITIES | DESIRED OUTCOMES | LEAD | TIMELINE |
| --- | --- | --- | --- | --- |
| Coordinate the implementation of the BSI-funded activities and complete the required reports. | Complete the basic skills plan, based on the year-long 2007-08 planning process. Coordinate the major BSI projects via the Steering Committee. Monitor progress and budget expenditures for each of the projects. | Complete and submit plan. Each project is addressed in light of plans/commitments for other BSI projects. Projects are completed as planned and budgeted and/or the plan it adjusted as needed. | Dan Henry Dan Henry, w/ project leads Dan Henry w/ project leads | Complete by: 10/15/08 Ongoing Ongoing |
| Complete the final phase of site planning for the college. | Work with the President and district facilities to secure architectural services. Establish a multi-constituency planning team. Site planning process. | Architectural services secured. Team established. Recommend completed site plan to SGC and the President. | Dan Henry; Peter Garcia Dan Henry Team chair or co-chairs | 12/08 – 1/09 1/09 2/09 – 5/09 |

| Work with the Steering Committee and key managers to update the Enrollment Management Plan to include strategies to further increase enrollment and improve productivity. | Steering Committee coordinates the work of subcommittees to update the plan. Plan reviewed and approved. | Updated plan developed. Constituencies review plan and provide input. Plan forwarded for approval by SGC and the Presdient. | Dan Henry Dan Henry | 12/08 - 3/09 4/09 – 5/09 |
| --- | --- | --- | --- | --- |